## RICs
ID | Description | Type | Date Identified | Impact | Probability | Importance | Response | Owner | Closure Date
1 | No development servers provided by I.S | Risk | 2020-01-20 | 200 | Medium | 100 | looking into alternative development servers | Tolu
2 | lose of project data | Risk | 2020-01-28 | 200 | Very Low | 20 | github repository created | Jon | 2020-01-28
3 | code for live Projex not accessible | Issue | 2020-01-23 | 200 |  | 200 | Mentioned to Brian in PM forum and sponser meeting. Failing that look into doing fresh Projex build with teams own code. *RESOLVED* | Karen | 2020-01-28
4 | understanding/training on python code for projex | Issue | 2020-01-20 | 100 |  | 100 | Training websites used by Brian to create live projex provided to be looked at by the team | Jon, Karen, Tolu, Greg, Nick | 2020-01-23
5 | Room is unavailable for group meeting | Issue | 2020-02-04 | 50 |  | 50 | Try to find another room or location to hold a meeting, even if it is just a quick 15 minute scrum. Failing that keep contact on Slack group chat. | Jon | 2020-02-04
6 | Room is unavailable for sponsor meeting | Issue | 2020-02-04 | 50 |  | 50 | Contact Brain to see if another time or date is suitable for Brain to hold a sponsor meeting. Failling that send an email with the 3 answers for the questions he asks in the meeting - What have you done? What will you do? Any obsticles?- from each team member. | Jon | 2020-02-04
7 | Servers do not function as required due to external factors. | Risk | 2020-02-04 | 200 | Very Low | 20 | Contact I.S to find out what the issue is and for an eta for the solution to be rectified. Set up a alternate server system for short term use if the servers will be down for an extended time. | Jon, Tolu
8 | Team members have assignments to do other than group project dividing their time. | Issue | 2020-02-04 | 25 |  | 25 | Try to plan the work load in advance for when the assignments are due so team members do not feel overburdened. Encourage team members to not leave any work until the last minute. | Jon, Karen, Tolu, Greg, Nick
9 | Team members have personal issues that make them unavailable to do work. | Issue | 2020-02-04 | 25 |  | 25 | Adjust the projects development where possible. Where possible get another team member to do the work if it is essential for projects progress. | Jon, Karen, Tolu, Greg, Nick
10 | Project development goes beyond agreed deadline/handover. | Risk | 2020-02-04 | 200 | Low | 60 | If project development looks like it will not reach completion before deadline/handover contact Brian to discuss extension possiblities. | Jon, Karen, Tolu, Greg, Nick
11